## Sheet1
assetID | AssetName | Task id | Task code | Task category | Task description | Note | Task dateApproved | Task approvedBy | Task status | Task initialDueDate | Task completedBy | Task dateCompleted | CreatedOn | createdBy | Task finalDueDate | Task reference | Task quantity | Task unitOfMeasure | Task unitRate | Task priority | Task type | Task class | Task reason | Task other | Task startDateTime | Task endDateTime | Task actualQuantity | Position_Lane | sysDateCompleted | sysCreatedOn | defect_axim_id | Category code | Class code | Code | Defect description | Instruction/Note
| Network | 214853.0554 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace raised kerb and channel o/s # 8 View Point Road, McCrae. As marked in the rain. |  | 2016-09-16 08:15 | Martin.Byrne | AVAILABLE | 2026-08-19 10:58 |  |  | 2016-08-19 10:56 | Gerard.Pillay | 2026-09-16 08:15 |  | 5 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 0 | NA |  | ############## | 214837.0554 | NKR | LS | KC01 | Replace raised kerb and channel o/s # 8 View Point Road, McCrae. As marked in the rain.
6833 | Network | 217759.0554 | RPT04 RPT04 - Digout Asphalt | A4.9 Local Shape Correction | Dig out required to repair cracking o/s # 6 View Point Road, McCrae. Marked. (7m x 2m) |  | 2017-09-13 09:00 | Martin.Byrne | AVAILABLE | 2027-08-14 09:39 |  |  | 2017-08-14 09:40 | Gerard.Pillay | 2027-09-13 09:00 |  | 14 | SQM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 14 | NA |  | 2017-08-14 09:40 | 217696.0554 | CRK | PM | RP03 | Dig out required to repair cracking o/s # 6 View Point Road, McCrae. Marked. (7m x 2m)
6833 | Network | 422.06 | MEC01 MEC01 - Make Safe | MEC - Call Out Service | 5 View Point Road MCCRAE | After Hours Callout ID: 28321541 |  |  | COMPLETED | 2021-08-31 10:25 | Jane.Piotrowski | 2021-07-31 09:28 | 2021-07-31 09:28 | Jane.Piotrowski | 2021-07-31 10:28 |  | 1 | HRS | 1 | 1H | FIND_N_FIX | LUMP_SUM |  |  |  |  | 1 | NA | 2021-08-02 09:29 | 2021-08-02 09:29 | 393.06 | 2001 | LUMP_SUM | MEC01 | 5 View Point Road MCCRAE | After Hours Callout ID: 28321541
[6 empty] | GR attended, assessed site and phoned through to Parks to attend | [29 empty] | GR attended, assessed site and phoned through to Parks to attend
[6 empty] | M# 2351120 | [29 empty] | M# 2351120
6833 | Network | 598.0613 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | View point road Mc Crae | Were speed hump has been cut ,please add ash to fill up the gap /ring Neil |  |  | COMPLETED | 2022-06-24 06:56 | Flocon1 | 2022-06-28 09:24 | 2022-06-10 06:59 | Neil.Robertson | 2022-06-24 06:56 |  | 2 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2022-06-28 09:24 | 2022-06-28 09:24 | 2 | NA | 2022-06-28 09:24 | 2022-06-10 06:59 | 605.0613 | 2010 | LUMP_SUM | PPR01 | View point road Mc Crae | Were speed hump has been cut ,please add ash to fill up the gap /ring Neil
6833 | Network | 257.758 | UHT04 UHT04 - Provisional Works | Unsealed Shoulder | View Point Rd to Penny Lane McCrae | Repair the gravel pathway with a 5mm Minus G rock, shaped & compacted between View Point Rd & Penny Lane McCrae | 2015-11-12 06:55 | Jane Piotrowski (SLR) | COMPLETED | 2020-11-12 | Carly.McCrohan | 2015-11-27 12:35 | 2015-11-12 06:50 | Andrew.Taylor | 2020-11-12 |  | 120 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 1899-12-31 12:35 | 1899-12-31 12:35 | 120 | NA | 2016-05-31 15:45 | 2015-11-12 06:53 | 261.758 | USHLD | PW | UH06 | View Point Rd to Penny Lane McCrae | Repair the gravel pathway with a 5mm Minus G rock, shaped & compacted between View Point Rd & Penny Lane McCrae
159251 | a_Outfall | 216014.0556 | OFT01 OFT01 - Open Outfall | Outfall | expose outfall on beach opp penny lane McCrae. On point nepean rd |  |  |  | COMPLETED | 2016-11-21 11:54 | Jane.Piotrowski | 2016-12-08 08:33 | 2016-11-07 11:54 | Alistair.White |  |  | 1 | LINM | 1 | 14D | PERMANENT | LS |  |  | 2016-12-12 08:34 | 2016-12-12 08:34 | 10 | NA | 2016-12-12 08:34 | ############## | 216004.0556 | OFALL | LS | OF01 | expose outfall on beach opp penny lane McCrae. On point nepean rd
1938 | Network | 478.0571 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | car park opp Penny lane Mccrae | car park opp Penny Lane ,drive in to car park the first parking spot on your right 1mt x2.5 were edge has broken away ,merit 2278556 |  |  | COMPLETED | 2021-01-20 14:13 | Flocon1 | 2021-01-15 09:08 | 2021-01-06 14:16 | Neil.Robertson | 2021-01-20 14:13 |  | 4 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2021-01-15 09:08 | 2021-01-15 09:08 | 4 | NA | 2021-01-15 09:08 | ############## | 484.0571 | PPR | LS | RP01 | car park opp Penny lane Mccrae | car park opp Penny Lane ,drive in to car park the first parking spot on your right 1mt x2.5 were edge has broken away ,merit 2278556
1938 | Network | 1954.0569 | MEC01 MEC01 - Make Safe | MEC - Call Out Service | Penny Lane McCrae | M#2505684 |  |  | COMPLETED | 2022-11-15 17:28 | Kylie.Crow1 | 2022-11-21 16:30 | 2022-11-15 16:29 | Kylie.Crow1 | 2022-11-15 17:29 |  | 1 | HRS | 1 | 1H | PERMANENT | LUMP_SUM |  |  | 2022-11-21 16:29 | 2022-11-21 16:30 | 1 | NA | 2022-11-21 16:30 | ############## | 1891.0569 | 2001 | LUMP_SUM | MEC01 | Penny Lane McCrae | M#2505684
[6 empty] | Call out id 31685288 | [29 empty] | Call out id 31685288
[6 empty] | A/hrs attended location and SES and Shire were already onsite, nfa req | [29 empty] | A/hrs attended location and SES and Shire were already onsite, nfa req
6833 | Network | 214661.0557 | LDT02 LDT02 - Provisional Works | Lined Drain | 2 View Point Rd & Prospect Hill Rd McCrae | Upgrade the 225mm pipeline at intersection with a 300mm black max pipeline | 2017-05-03 12:58 | Andrew.Taylor | COMPLETED | 2022-05-03 08:21 | Michelle.Twaites | 2017-05-30 09:16 | 2017-05-03 08:29 | Andrew.Taylor | 2022-05-03 12:58 |  | 36 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 2017-05-31 09:16 | 2017-05-31 09:16 | 36 | NA | 2017-05-31 09:16 | 2017-05-03 08:30 | 214650.0557 | LDRAIN | PW | LD04 | 2 View Point Rd & Prospect Hill Rd McCrae | Upgrade the 225mm pipeline at intersection with a 300mm black max pipeline
[6 empty] | Raise road reserve along Prospect Hill Rd to protect property | [29 empty] | Raise road reserve along Prospect Hill Rd to protect property
[6 empty] | Build a levy bank at the back of the SEP in Prospect Hill Rd in front of the gates (levy will be high than gates preventing usage) | [29 empty] | Build a levy bank at the back of the SEP in Prospect Hill Rd in front of the gates (levy will be high than gates preventing usage)
[6 empty] | Reconnect disused SEP in View Point Rd with flutes & create levy at rear to protect lower property | [29 empty] | Reconnect disused SEP in View Point Rd with flutes & create levy at rear to protect lower property
4301 | Network | 790.0574 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | Pothole repairs o/s 1 Prospect Hill Rd, cnr Coburn Ave McCrae. Marked. Damaged asphalt on Prospect Hill Rd | Please remove loose sections of damaged asphalt. Refer to pictures |  |  | COMPLETED | 2019-02-19 12:12 | David.Norton | 2019-02-06 15:43 | 2019-02-05 12:16 | Gerard.Pillay | 2019-02-19 12:16 |  | 2.42 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2019-02-06 15:43 | 2019-02-06 15:43 | 2.42 | NA | 2019-02-06 15:43 | ############## | 774.0574 | PPR | LS | RP01 | Pothole repairs o/s 1 Prospect Hill Rd, cnr Coburn Ave McCrae. Marked. Damaged asphalt on Prospect Hill Rd | Please remove loose sections of damaged asphalt. Refer to pictures
6833 | Network | 791.0574 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace damaged k & c o/s 1 View Pt Rd McCrae.cnr Prospect Hill Rd, in View Pt side. Marked |  | 2019-02-15 13:32 | Chris.Godsil | AVAILABLE | 2019-04-06 12:28 |  |  | 2019-02-05 12:32 | Gerard.Pillay | 2029-02-15 13:32 |  | 6 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 6 | NA |  | ############## | 775.0574 | NKR | LS | KC02 | Replace damaged k & c o/s 1 View Pt Rd McCrae.cnr Prospect Hill Rd, in View Pt side. Marked
4301 | Network | 133.4157 | PTT06 PTT06 - Reset Lid | A4.18 Pit / Drainage Structure Repair | 11 Prospect Hill Road, MCCRAE | RRT Sth attended location and reset pit lid back into place. |  |  | COMPLETED | 2019-05-08 15:59 | Rachel.Larsen | 2019-05-08 12:01 | 2019-05-08 12:01 | Rachel.Larsen | 2019-05-22 12:01 |  | 1 | ITEM | 1 | 14D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2019-05-09 12:02 | ############## | 103.4157 | DPR | LS | PT04 | 11 Prospect Hill Road, MCCRAE | RRT Sth attended location and reset pit lid back into place.
[6 empty] | Merit2070668 | [29 empty] | Merit2070668
4301 | Network | 2035.0593 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | 1 x pothole , beside kerb , o/s # 14 Prospect Hill rd . |  |  |  | COMPLETED | 2020-03-05 09:34 | Flocon1 | 2020-03-04 13:54 | 2020-02-20 09:35 | Glenn.Richardson2 | 2020-03-05 09:35 |  | 0.8 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2020-03-04 13:54 | 2020-03-04 13:54 | 0.8 | NA | 2020-03-04 13:54 | 2020-02-20 09:35 | 2030.0593 | PPR | LS | RP01 | 1 x pothole , beside kerb , o/s # 14 Prospect Hill rd .
4301 | Network | 643.0571 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | Prospect Hill Rd, Mccrae | Repair pothole O/S #1 merit #2317841 |  |  | COMPLETED | 2021-04-28 14:21 | Flocon1 | 2021-04-19 13:59 | 2021-04-14 14:23 | Neil.Robertson | 2021-04-28 14:21 |  | 1 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2021-04-19 13:59 | 2021-04-19 13:59 | 1 | NA | 2021-04-19 14:00 | ############## | 651.0571 | 2010 | LUMP_SUM | PPR01 | Prospect Hill Rd, Mccrae | Repair pothole O/S #1 merit #2317841
4301 | Network | 970.0613 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | prospect hill McCrae | please repair broken asphalt in front of #1 /merit 2514786 |  |  | COMPLETED | 2022-12-30 10:55 | Flocon1 | 2023-01-03 11:58 | 2022-12-16 10:58 | Neil.Robertson | 2022-12-30 10:55 |  | 2 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-01-03 11:48 | 2023-01-03 11:58 | 2 | NA | 2023-01-03 11:58 | ############## | 994.0613 | 2010 | LUMP_SUM | PPR01 | prospect hill McCrae | please repair broken asphalt in front of #1 /merit 2514786
4301 | Network | 305.4179 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | 1 Prospect Hill Road McCrae | CLEAN 1x previous pothole repair and re do. M2514786 |  |  | COMPLETED | 2023-02-07 13:56 | Flocon1 | 2023-02-03 10:39 | 2023-01-24 13:58 | Courtney.Verhagen | 2023-02-07 13:58 |  | 0.1 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-02-03 10:20 | 2023-02-03 10:39 | 0.1 | NA | 2023-02-03 10:41 | ############## | 308.4179 | 2010 | LUMP_SUM | PPR01 | 1 Prospect Hill Road McCrae | CLEAN 1x previous pothole repair and re do. M2514786
6320 | Network | 214506.0548 | BWT02 BWT02 - Replace Bolts or Nails | Board Walk, Jetty, LookOut, Stairs | The Eyrie, MCCRAE | Patrol Crew attended and screwed in loose back board at top of stairs |  |  | COMPLETED | 2017-02-09 08:00 | Jane.Piotrowski | 2017-01-10 08:00 | 2017-01-10 08:00 | Jane.Piotrowski | 2017-02-09 08:00 |  | 1 | ITEM | 1 | 30D | FIND_N_FIX | LS |  |  | 2017-01-11 08:02 |  | 1 | NA | 2017-01-11 08:02 | 2017-01-11 08:02 | 214441.0548 | BWALK | LS | BW01 | The Eyrie, MCCRAE | Patrol Crew attended and screwed in loose back board at top of stairs
6320 | Network | 217754.0554 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replaced damaged kerb and channel o/s # 1 The Eyrie corner Wonga Grove, McCrae. Damaged kerb and channel on the corner. Marked in the rain. |  | 2017-09-13 09:00 | Martin.Byrne | COMPLETED | 2027-08-11 13:40 | Mark.Coward | 2019-08-03 10:32 | 2017-08-11 13:42 | Gerard.Pillay | 2027-09-13 09:00 |  | 16 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 16 | NA | 2019-08-03 10:34 | ############## | 217692.0554 | NKR | PM | KC02 | Replaced damaged kerb and channel o/s # 1 The Eyrie corner Wonga Grove, Maccrae. Damaged kerb and channel on the corner. Marked in the rain.
6320 | Network | 2354.0565 | RPT02 RPT02 - Repair Edge Break | A4.12 Edge Break Repair | cnr THE EYRIE & WONGA GV | Repair edge break & k&c while waiting for replacement. |  |  | COMPLETED | 2018-06-07 13:26 | Flocon1 | 2018-05-16 09:13 | 2018-02-07 13:26 | Mark.Coward |  |  | 1.5 | LINM | 1 | 120D | PERMANENT | LS |  |  | 2018-05-16 09:13 | 2018-05-16 09:13 | 1.5 | NA | 2018-05-16 09:14 | ############## | 2365.0565 | SEB | LS | RP02 | cnr THE EYRIE & WONGA GV | Repair edge break & k&c while waiting for replacement.
6320 | Network | 218862.0553 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie McCrae | 16/3 Patrol Crew attended and replaced 5 tread boards. |  |  | COMPLETED | 2018-04-15 11:50 | Carly.McCrohan | 2018-03-16 11:51 | 2018-03-16 11:51 | Carly.McCrohan | 2018-04-15 11:50 |  | 1 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2018-03-20 11:51 | ############## | 216534.0553 | BWALK | LS | BW02 | The Eyrie McCrae | 16/3 Patrol Crew attended and replaced 5 tread boards.
2077 | Network | 217602.0555 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie Stairs, MCCRAE | Response crew to replace tread as marked and have a look at missing bolts. |  |  | COMPLETED | 2018-04-26 15:02 | Patrol1 | 2018-04-04 09:55 | 2018-03-27 15:03 | Natalie.Renouf | 2018-04-26 15:03 |  | 1 | LINM | 1 | 30D | PERMANENT | LS |  |  | 2018-04-04 09:55 | 2018-04-04 09:55 | 1 | NA | 2018-04-04 09:55 | ############## | 217433.0555 | BWALK | LS | BW02 | The Eyrie Stairs, MCCRAE | Response crew to replace tread as marked and have a look at missing bolts.
2077 | Network | 274.057 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie, MCCRAE | Patrol Crew replaced 1 x damaged treadboard on The Eyrie Steps as find & fix |  |  | COMPLETED | 2018-07-13 15:38 | Jane.Piotrowski | 2018-06-13 15:38 | 2018-06-13 15:40 | Jane.Piotrowski | 2018-07-13 15:40 |  | 2 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 2 | NA | 2018-06-13 15:40 | ############## | 49.057 | BWALK | LS | BW02 | The Eyrie, MCCRAE | Patrol Crew replaced 1 x damaged treadboard on The Eyrie Steps as find & fix
6320 | Network | 1.4159 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | 15 The Eyrie, MCCRAE | Crew attended location and replaced step boards |  |  | COMPLETED | 2019-02-15 09:39 | Kylie.Crow1 | 2019-01-16 09:42 | 2019-01-16 09:42 | Kylie.Crow1 | 2019-02-15 09:39 |  | 4 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 4 | NA | 2019-01-17 09:43 | 2019-01-17 09:43 | 1.4159 | BWALK | LS | BW02 | 15 The Eyrie, MCCRAE | Crew attended location and replaced step boards
[6 empty] | Merit 2027377 | [29 empty] | Merit 2027377
6320 | Network | 220189.0553 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | 15 The Eyrie MCCRAE | RRT attended and fixed the step |  |  | COMPLETED | 2019-02-17 16:00 | Carly.McCrohan | 2019-01-18 16:01 | 2019-01-18 16:01 | Carly.McCrohan | 2019-02-17 16:00 |  | 1 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2019-01-21 16:02 | ############## | 217046.0553 | BWALK | LS | BW02 | 15 The Eyrie MCCRAE | RRT attended and fixed the step
222800 | a_FootpathLow | 220262.0552 | SRT06 SRT06 - Concrete Replacement | A4.22 Maintenance of Path | Replace 2 cracking concrete steps 20m from the top of The Eyrie Steps public walk-way . |  |  |  | AVAILABLE | 2019-06-28 13:05 |  |  | 2019-05-29 13:08 | Gerard.Pillay | 2029-05-29 13:08 |  | 1.5 | SQM |  | 10Y | PERMANENT | PM |  |  |  |  | 1.5 | NA |  | ############## | 220266.0552 | RFK | LS | SR02 | Replace 2 cracking concrete steps 20m from the top of The Eyrie Steps public walk-way .
6320 | Network | 243.0591 | BWT09 BWT09 - Provisional Works | Board Walk, Jetty, LookOut, Stairs | The Eyrie McCrae - Stairs | Remove the rotted and failing timber edge strips to the concrete steps & replace with new timbers |  |  | COMPLETED | 2025-01-27 09:08 | Andrew.Taylor | 2020-03-03 12:00 | 2020-01-27 09:10 | Andrew.Taylor | 2025-01-27 09:10 |  | 8 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 2020-01-30 12:00 | 2020-03-03 12:00 | 8 | NA | 2020-03-31 09:42 | 2020-03-31 09:11 | 246.0591 | BWALK | PW | BW05 | The Eyrie McCrae - Stairs | Remove the rotted and failing timber edge strips to the concrete steps & replace with new timbers
6320 | Network | 2034.0593 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace 2m f damaged kerb & channel on cnr of Wonga gv & The Eyrie . |  |  |  | AVAILABLE | 2020-04-20 09:28 |  |  | 2020-02-20 09:30 | Glenn.Richardson2 | 2030-02-20 09:30 |  | 2 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 2 | NA |  | 2020-02-20 09:30 | 2029.0593 | NKR | LS | KC02 | Replace 2m f damaged kerb & channel on cnr of Wonga gv & The Eyrie .
170536 | a_Stairs | 422.0613 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | 22 The Eyrie McCrae | Replace 2x Timbers. Marked. Merit #2428553 & #2430785 |  |  | COMPLETED | 2022-04-06 13:54 | .CREW MAINTENANCE | 2022-04-06 07:29 | 2022-03-07 13:55 | Neil.Robertson | 2022-04-06 13:55 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-04-06 07:29 | 2022-04-06 07:29 | 1 | NA | 2022-04-06 07:29 | ############## | 425.0613 | 2021 | LUMP_SUM | RFK01 | 22 The Eyrie McCrae | Replace 2x Timbers. Marked. Merit #2428553
170536 | a_Stairs | 255.0609 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | The Eyrie Stairs McCrae | RRT replaced 1 x tread |  |  | COMPLETED | 2022-07-15 16:40 | .CREW MAINTENANCE | 2022-07-01 16:42 | 2022-07-01 16:41 | Michelle.Twaites | 2022-07-31 16:41 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-07-01 16:42 | 2022-07-01 16:42 | 1 | NA | 2022-07-04 16:43 | ############## | 253.0609 | 2021 | LUMP_SUM | RFK01 | The Eyrie Stairs McCrae | RRT replaced 1 x tread
6320 | Network | 1820.0569 | MEC01 MEC01 - Make Safe | MEC - Call Out Service | 17 The Eyrie, Mccrae | Sink hole in driveway made safe with stake and parawebbing by Rapid South. M#2485946. |  |  | COMPLETED | 2022-09-20 11:10 | .CREW MAINTENANCE | 2022-09-14 10:08 | 2022-09-14 10:08 | Kylie.Crow1 | 2022-09-20 11:10 |  | 1 | HRS | 1 | 1H | FIND_N_FIX | LUMP_SUM |  |  | 2022-09-14 10:06 | 2022-09-14 10:08 | 1 | NA | 2022-09-20 10:10 | ############## | 1757.0569 | 2001 | LUMP_SUM | MEC01
6518 | a_Pipe | 948.0591 | DLD03 DLDT03 - Repair Lined Drain | DLD - Minor Repair Lined Drains | 17 The Eyrie McCrae | Investigated sink hole in driveway & found pipe displacement. |  |  | COMPLETED | 2022-11-02 07:25 | Andrew.Taylor | 2022-10-12 07:30 | 2022-10-03 07:27 | Andrew.Taylor | 2022-11-02 07:27 |  | 2.4 | LINM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-10-11 07:30 | 2022-10-12 07:30 | 2.4 | NA | 2022-10-12 07:30 | 2022-10-12 07:29 | 933.0591 | 2006 | LUMP_SUM | DLD01 | 17 The Eyrie McCrae | Investigated sink hole in driveway & found pipe displacement.
[6 empty] | Repaired & reinstated all areas effected (ID: 2485946) | [29 empty] | Repaired & reinstated all areas effected (ID: 2485946)
63930 | a_Pit | 1519.4201 | DPR10 DPR10 - Make Safe | DPR - Pit/Drainage Structure Repair | 17 The Eyrie MCCRAE | Rapid SOuth attended and advised made safe with stake and tape. |  |  | COMPLETED | 2023-10-26 19:30 | G_MPSC_RapidSouth1 | 2023-10-26 15:00 | 2023-10-26 14:40 | Lalah.Farhang | 2023-10-26 18:40 |  | 1 | ITEM | 1 | 4H | PERMANENT | LUMP_SUM |  |  | 2023-10-26 14:40 | 2023-10-26 15:00 | 1 | NA | 2023-10-26 15:31 | ############## | 1057.4201 | 2008 | LUMP_SUM | DPR01 | 17 The Eyrie MCCRAE | new lid required. 005505
5505
63930 | a_Pit | 1518.4201 | DPR01 DPR01 - Replace Lid | DPR - Pit/Drainage Structure Repair | 17 The Eyrie MCCRAE | new lid required. 005505 |  |  | AVAILABLE | 2023-10-26 19:30 |  |  | 2023-10-26 15:31 | Lalah.Farhang | 2033-10-26 15:31 |  | 1 | ITEM |  | 10Y | PERMANENT | SOR | [5 empty] | NA |  | ############## | 1057.4201 | 2008 | LUMP_SUM | DPR01 | 17 The Eyrie MCCRAE | new lid required. 005505
170536 | a_Stairs | 1114.4179 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | 20-22 The Eyrie Stairs McCrae | Replace 3x timbers along front of concrete stairs. . approx 1350x75x200. 010546 |  |  | COMPLETED | 2024-03-17 14:41 | Patrol1 | 2024-03-14 10:30 | 2024-02-16 14:42 | Courtney.Verhagen | 2024-03-17 14:42 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2024-03-14 08:45 | 2024-03-14 10:30 | 1 | NA | 2024-03-14 10:30 | ############## | 1119.4179 | 2021 | LUMP_SUM | RFK01 | 20-22 The Eyrie Stairs McCrae | Replace 3x timbers along front of concrete stairs. . approx 1350x75x200. 010546