## Coburn Ave
Task dateApproved | Task approvedBy | Task status | Task initialDueDate | Task completedBy | Task dateCompleted | CreatedOn | createdBy | Task finalDueDate | Task reference | Task quantity | Task unitOfMeasure | Task unitRate | Task priority | Task type | Task class | Task reason | Task other | Task startDateTime | Task endDateTime | Task actualQuantity | Position_Lane | sysDateCompleted | sysCreatedOn | defect_axim_id | Category code | Class code | Code | Defect description | Instruction/Note
2017-09-13 09:00 | Martin.Byrne | AVAILABLE | 2027-08-11 14:24 |  |  | 2017-08-11 14:26 | Gerard.Pillay | 2027-09-13 09:00 |  | 126.9 | SQM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 126.9 | NA |  | 2017-08-11 14:27 | 217695.0554 | CRK | PM | RP03 | Dig out required to repair cracking o/s # 637 Point Nepean Road corner Coburn Avenue, McCrae. Cracking on Coburn Avenue. Marked in the rain. (47m x 2.7m)
2019-02-14 11:00 | Jane.Piotrowski | COMPLETED | 2028-11-07 12:25 | Lalah.Farhang | 2023-08-25 11:05 | 2018-11-07 12:27 | Michelle.Twaites | 2029-02-14 11:00 |  | 1 | ITEM | 1 | 10Y | PERMANENT | PM |  |  | 2023-08-25 11:04 | 2023-08-25 11:05 | 1 | NA | 2023-08-25 11:06 | 2018-11-07 12:27 | 215940.0562 | DPR | PM | PT02 | 11 Coburn Ave Mccrae | Replace lintel at 11 Coburn Ave
2019-02-14 11:00 |  | COMPLETED | 2028-11-07 12:27 | Ryan.Griffiths | 2023-07-11 16:07 | 2018-11-07 12:30 | Michelle.Twaites | 2029-02-14 10:59 |  | 1 | ITEM | 1 | 10Y | PERMANENT | PM |  |  | 2023-07-11 16:07 | 2023-07-11 16:07 | 1 | NA | 2023-08-16 16:08 | 2018-11-07 12:30 | 215941.0562 | DPR | PM | PT02 | 10 Coburn Ave McCrae | Replace lintel at 10 Coburn Ave (opp 11)
|  | CANCELLED | 2030-02-20 09:21 |  |  | 2020-02-20 09:23 | Glenn.Richardson2 | 2030-02-20 09:23 |  | 38.4 | SQM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 38.4 | NA |  | 2020-02-20 09:24 | 2028.0593 | CRK | PM | RP03 | Repair cracking o/s # 9 Coburn ave .
|  | COMPLETED | 2030-08-17 08:14 | .CREW MAINTENANCE | 2022-08-05 13:37 | 2020-08-17 08:16 | Mark.Coward | 2030-08-17 08:16 |  | 1 | ITEM | 1 | 10Y | PERMANENT | PM |  |  | 2022-08-05 13:37 | 2022-08-05 13:37 | 1 | NA | 2022-08-05 13:39 | 2020-08-17 08:17 | 2457.059 | DPR | PM | PT02 | o/s # 1 cnr burrell st & coburn ave McCrae
|  | COMPLETED | 2022-06-04 07:58 | Patrol1 | 2022-05-25 09:11 | 2022-05-05 08:01 | Gerard.Pillay | 2022-06-04 08:01 |  | 1 | SQM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-05-25 09:11 | 2022-05-25 09:11 | 1 | NA | 2022-05-25 09:11 | 2022-05-05 08:02 | 3827.0592 | 2021 | LUMP_SUM | RFK01 | Wedge exposed aggregate bay o/s # 635 Point Nepean Road corner Coburn Avenue, McCrae. Wedge on Point Nepean Road. Marked.
|  | COMPLETED | 2022-08-12 12:34 | .CREW MAINTENANCE | 2022-08-11 11:34 | 2022-08-11 11:34 | Michelle.Twaites | 2022-08-12 12:34 |  | 1 | HRS | 1 | 1H | FIND_N_FIX | LUMP_SUM |  |  | 2022-08-11 11:22 | 2022-08-11 11:34 | 1 | NA | 2022-08-12 11:34 | 2022-08-12 11:34 | 273.0609 | 2001 | LUMP_SUM | MEC01
|  | COMPLETED | 2022-08-12 15:36 | Paveline1 | 2024-04-30 11:03 | 2022-08-12 11:37 | Michelle.Twaites | 2032-08-12 11:37 |  | 1 | ITEM |  | 10Y | PERMANENT | SOR |  |  | 2024-04-30 10:35 | 2024-04-30 11:03 | 1 | NA | 2024-04-30 11:03 | 2022-08-12 11:38 | 274.0609 | 2008 | LUMP_SUM | DPR01 | 4 Coburn Ave McCrae | replace std lid M#2474727
|  | AVAILABLE | 2022-08-14 11:38 |  |  | 2022-08-12 11:41 | Michelle.Twaites | 2032-08-12 11:41 |  | 1 | ITEM |  | 10Y | PERMANENT | SOR |  |  |  |  | 1 | NA |  | 2022-08-12 11:42 | 275.0609 | 2008 | LUMP_SUM | DPR01 | 4 Coburn Ave McCrae | Replace medium surround 1200 x 750 M#2474727
|  | COMPLETED |  | G_MPSC_RapidSouth1 | 2022-09-01 08:55 | 2022-09-01 08:55 | G_MPSC_RapidSouth1 | 2022-09-04 08:55 |  | 0.4 | SQM | 1 | 3D | FIND_N_FIX | LUMP_SUM |  |  | 2022-09-01 08:55 | 2022-09-01 08:55 | 0.4 |  | 2022-09-01 08:55 | 2022-09-01 08:55 | 89.4199 | 2028 | LUMP_SUM | RLC01
|  | COMPLETED | 2022-11-07 16:16 | .CREW MAINTENANCE | 2022-11-07 12:19 | 2022-11-07 12:18 | Lalah.Farhang | 2022-11-07 16:18 |  | 1 | ITEM | 1 | 4H | PERMANENT | LUMP_SUM |  |  | 2022-11-07 12:19 | 2022-11-07 12:19 | 1 | NA | 2022-11-08 12:20 | 2022-11-08 12:19 | 48.4201 | 2008 | LUMP_SUM | DPR01 | 10 Coburn Avenue, Mccrae | Rapid North attended made it safe via stake and tape. M#2501774
|  | COMPLETED | 2022-11-19 10:51 | Andrew.Taylor | 2022-11-24 07:01 | 2022-11-19 06:59 | Andrew.Taylor | 2032-11-19 06:59 |  | 1 | ITEM | 1 | 10Y | PERMANENT | SOR |  |  | 2022-11-19 07:00 | 2022-11-24 07:01 | 1 | NA | 2022-12-21 07:01 | 2022-12-21 07:01 | 977.0591 | 2008 | LUMP_SUM | DPR01 | 24 Coburn Ave McCrae | Removed the sunken & dropped JP. Reinstated JP & connected property outlet pipe back into the pit & reinstated road reserve
|  | COMPLETED | 2023-02-15 15:12 | Kylie.Crow1 | 2023-02-21 11:14 | 2023-02-15 11:13 | Kylie.Crow1 | 2023-02-15 15:13 |  | 1 | ITEM | 1 | 4H | PERMANENT | LUMP_SUM |  |  | 2023-02-21 11:13 | 2023-02-21 11:14 | 1 | NA | 2023-02-21 11:14 | 2023-02-21 11:14 | 2211.0569 | 2008 | LUMP_SUM | DPR01 | 38 Coburn Ave McCrae | M#2540607 A/hrs attended location and reset pit lid to make safe
|  | COMPLETED | 2023-03-02 11:11 | Flocon2 | 2023-02-27 13:08 | 2023-02-16 11:14 | Glenn.Richardson2 | 2023-03-02 11:14 |  | 1.2 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-02-27 13:02 | 2023-02-27 13:08 | 1.2 | NA | 2023-02-27 13:10 | 2023-02-16 11:15 | 11340.0593 | 2010 | LUMP_SUM | PPR01 | On Coburn Ave , 50m in from Pt Nep Rd . | 3 x potholes .
|  | COMPLETED | 2023-03-02 13:13 | Flocon2 | 2023-02-27 12:48 | 2023-02-16 13:15 | Glenn.Richardson2 | 2023-03-02 13:15 |  | 0.4 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-02-27 12:45 | 2023-02-27 12:48 | 0.4 | NA | 2023-02-27 12:48 | 2023-02-16 13:15 | 11341.0593 | 2010 | LUMP_SUM | PPR01 | o/s # 9 Coburn Ave . | 1 x pothole .
|  | COMPLETED | 2023-08-12 14:47 | Paveline1 | 2024-05-08 10:30 | 2023-04-14 14:52 | Gerard.Pillay | 2023-08-12 14:52 |  | 234 | LINM | 1 | 120D | PERMANENT | LUMP_SUM |  |  | 2024-05-08 08:00 | 2024-05-08 10:30 | 234 | NA | 2024-05-20 08:16 | 2023-04-14 14:53 | 6638.0592 | 2012 | LUMP_SUM | PCS01 | On Coburn Avenue o/s and between # 637 Point Nepean Road and # 639 Coburn Avenue, McCrae. | Paveline required to repair cracking. Marked (78m x 3m)
|  | COMPLETED | 2023-08-12 14:53 | Paveline1 | 2024-05-08 13:30 | 2023-04-14 14:55 | Gerard.Pillay | 2023-08-12 14:55 |  | 43.5 | LINM | 1 | 120D | PERMANENT | LUMP_SUM |  |  | 2024-05-08 11:30 | 2024-05-08 13:30 | 80 | NA | 2024-05-20 08:18 | 2023-04-14 14:56 | 6639.0592 | 2012 | LUMP_SUM | PCS01 | O/s the driveway area of # 3A Coburn Avenue, McCrae. | Paveline required to repair cracking. Marked. (15m x 2.9m)
|  | COMPLETED | 2023-08-12 14:56 | Paveline1 | 2024-05-08 15:30 | 2023-04-14 14:57 | Gerard.Pillay | 2023-08-12 14:57 |  | 106 | LINM | 1 | 120D | PERMANENT | LUMP_SUM |  |  | 2024-05-08 13:30 | 2024-05-08 15:30 | 106 | NA | 2024-05-20 08:19 | 2023-04-14 14:58 | 6640.0592 | 2012 | LUMP_SUM | PCS01 | O/s the driveway area of # 1 Coburn Avenue, McCrae. | Paveline required to repair cracking. Marked. (34m x 3.1m)
|  | COMPLETED | 2023-07-08 14:43 | Lalah.Farhang | 2023-08-25 10:52 | 2023-07-01 14:44 | Andrew.Wall | 2033-07-01 14:44 |  | 1 | ITEM | 1 | 10Y | PERMANENT | SOR |  |  | 2023-08-25 10:51 | 2023-08-25 10:52 | 1 | NA | 2023-08-25 10:53 | 2023-08-09 14:46 | 35.4104 | 2008 | LUMP_SUM | DPR01 | 7 Coburn Ave McCrae
|  | COMPLETED | 2024-02-28 13:57 | Flocon1 | 2024-02-21 12:48 | 2024-02-14 13:58 | Glenn.Richardson2 | 2024-02-28 13:58 |  | 0.1 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2024-02-21 12:43 | 2024-02-21 12:48 | 0.1 | NA | 2024-02-21 12:48 | 2024-02-14 13:59 | 14016.0593 | 2010 | LUMP_SUM | PPR01 | On Coburn Ave , 50m in from Pt Nep Rd . | 1 x small pothole .
|  | COMPLETED | 2024-05-24 08:29 | .SUB CONTRACTOR | 2024-05-09 12:00 | 2024-05-09 10:30 | Lalah.Farhang | 2034-05-09 10:30 |  | 1 | SQM | 1 | 10Y | PERMANENT | SOR |  |  | 2024-05-09 10:30 | 2024-05-09 12:00 | 1 | NA | 2024-05-21 08:32 | 2024-05-21 08:32 | 1665.4201 | 2028 | LUMP_SUM | RLC01 | Roasbud Foreshore - Opp Coburn Ave, McCrae | ASE removed concrete. M#2024-037269
|  | COMPLETED | 2024-06-12 07:48 | .SUB CONTRACTOR | 2024-05-29 13:30 | 2024-05-15 07:55 | Courtney.Verhagen | 2024-06-12 07:55 |  | 400 | SQM | 1 | 28D | PERMANENT | LUMP_SUM |  |  | 2024-05-29 13:20 | 2024-05-29 13:30 | 400 | NA | 2024-05-29 14:51 | 2024-05-15 07:56 | 1250.4179 | 2019 | LUMP_SUM | PSW01 | 3 Coburn Avenue McCrae | Sweep loose rock from reseal works. 400m area.

## Propect Hill, Eyrie, Penny Etc
assetID | AssetName | Task id | Task code | Task category | Task description | Note | Task dateApproved | Task approvedBy | Task status | Task initialDueDate | Task completedBy | Task dateCompleted | CreatedOn | createdBy | Task finalDueDate | Task reference | Task quantity | Task unitOfMeasure | Task unitRate | Task priority | Task type | Task class | Task reason | Task other | Task startDateTime | Task endDateTime | Task actualQuantity | Position_Lane | sysDateCompleted | sysCreatedOn | defect_axim_id | Category code | Class code | Code | Defect description | Instruction/Note
159897 | a_Carpark | 3378.761 | RPT02 RPT02 - Repair Edge Break | A4.12 Edge Break Repair | sealed car pk entry oppo margaret av mccrae next to ped xing | e/break repair @ entry to car park next to ped xing 0.5 |  |  | COMPLETED | 2014-09-14 | Michelle.Twaites | 2014-07-01 11:50 | 2014-06-16 11:10 | Gary.Harrison | 2014-09-14 |  | 0.5 | LINM | 1 | 90D | PERMANENT | LS |  |  | 1899-12-31 11:45 | 1899-12-31 11:50 | 0.5 | NA | 2016-05-31 15:46 | 2014-06-16 11:12 | 3702.761 | SEB | LS | RP02 | sealed car pk entry oppo margaret av mccrae next to ped xing | e/break repair @ entry to car park next to ped xing 0.5
159897 | a_Carpark | 5320.753 | RPT05 RPT05 - Repair Cracking | A4.3.3 Cracking | repair croc cracking as you enter carpark on beach opp Margaret st McCrae. Pt nepean rd McCrae. 5m x 2m |  |  |  | COMPLETED | 2015-09-11 | Carly.McCrohan | 2014-12-09 14:45 | 2014-09-11 10:53 | Alistair.White | 2015-09-11 |  | 10 | SQM | 1 | 365D | PERMANENT | LS |  |  | 1899-12-31 14:25 | 1899-12-31 14:45 | 4 | NA | 2016-05-31 15:46 | 2014-09-11 10:56 | 5912.753 | CRK | LS | RP03 | repair croc cracking as you enter carpark on beach opp Margaret st McCrae. Pt nepean rd McCrae. 5m x 2m
4795 | Network | 4674.764 | URT01 URT01 - Gravel Patch | Unsealed Road Pavement | Margaret Street, MCCRAE | Gravel patching potholes as per MVenturin (20sqm) - find & fix |  |  | COMPLETED | 2015-08-13 | Carly.McCrohan | 2015-07-16 14:19 | 2015-07-16 14:19 | Carly.McCrohan | 2015-08-13 |  | 20 | SQM | 1 | 28D | FIND_N_FIX | LS |  |  |  |  | 20 | NA | 2015-07-17 14:21 | 2015-07-17 14:21 | 4731.764 | UPAVT | LS | UR05 | Margaret Street, MCCRAE | Gravel patching potholes as per MVenturin (20sqm) - find & fix
6320 | Network | 1576.76 | MST11 MST11 - Make Safe – Other Works | Make Safe | 1 The Eyrie McCrae | Response Crew picked up hazard signs as requested by NR. |  |  | COMPLETED | 2015-08-11 | Jane.Piotrowski | 2015-08-10 16:55 | 2015-08-10 16:55 | Jane.Piotrowski | 2015-08-11 |  | 1 | ITEM | 1 | 1D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2015-08-10 16:57 | 2015-08-10 16:57 | 288.76 | MSAFE | LS | MS01 | 1 The Eyrie McCrae | Response Crew picked up hazard signs as requested by NR.
6833 | Network | 255.758 | UPT02 UPT02 - Reinstate Path | A4.22 Maintenance of Path | View Point Rd to Penny Lane, McCrae | Repair the gravel pathway with a 5 mm Minus G rock between View point & Penny Lane | 2015-11-11 15:29 | Jane Piotrowski (SLR) | COMPLETED | 2015-12-11 | Carly.McCrohan | 2015-11-19 14:10 | 2015-11-11 15:09 | Andrew.Taylor | 2025-11-11 |  | 120 | SQM | 1 | 10Y | PERMANENT | PM |  |  | 1899-12-31 14:10 | 1899-12-31 14:10 | 120 | NA | 2016-05-31 15:46 | 2015-11-11 15:19 | 258.758 | RFK | LS | UP05
6833 | Network | 257.758 | UHT04 UHT04 - Provisional Works | Unsealed Shoulder | View Point Rd to Penny Lane McCrae | Repair the gravel pathway with a 5mm Minus G rock, shaped & compacted between View Point Rd & Penny Lane McCrae | 2015-11-12 06:55 | Jane Piotrowski (SLR) | COMPLETED | 2020-11-12 | Carly.McCrohan | 2015-11-27 12:35 | 2015-11-12 06:51 | Andrew.Taylor | 2020-11-12 |  | 120 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 1899-12-31 12:35 | 1899-12-31 12:35 | 120 | NA | 2016-05-31 15:46 | 2015-11-12 06:54 | 261.758 | USHLD | PW | UH06 | View Point Rd to Penny Lane McCrae | Repair the gravel pathway with a 5mm Minus G rock, shaped & compacted between View Point Rd & Penny Lane McCrae
4795 | Network | 6282.757 | URT01 URT01 - Gravel Patch | Unsealed Road Pavement | Margaret Street, McCrae | Bobcat to repair potholes at intersection of Pt Nepean Rd |  |  | COMPLETED | 2016-04-07 | Natalie.Renouf | 2016-04-05 15:05 | 2016-03-10 10:21 | Natalie.Renouf | 2016-04-07 |  | 1 | SQM | 1 | 28D | PERMANENT | LS |  |  | 1899-12-31 15:05 | 1899-12-31 15:05 | 30 | NA | 2016-05-31 15:46 | 2016-03-10 10:25 | 6389.757 | UPAVT | LS | UR05 | Margaret Street, McCrae | Bobcat to repair potholes at intersection of Pt Nepean Rd
2890 | Network | 214854.0554 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace damaged kerb and channel o/s # 17 The Eyrie, corner Coburn Avenue, McCrae. Damaged kerb and channel on Coburn Avenue. Close to the corner. In front of storm water pit. As marked in the rain. |  | 2016-09-16 08:15 | Martin.Byrne | COMPLETED | 2026-08-19 11:14 | Mark.Coward | 2019-08-03 10:37 | 2016-08-19 11:10 | Gerard.Pillay | 2026-09-16 08:15 |  | 1.8 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 1.8 | NA | 2019-08-03 10:40 | 2016-08-19 11:14 | 214838.0554 | NKR | LS | KC02 | Replace damaged kerb and channel o/s # 17 The Eyrie, corner Coburn Avenue, McCrae. Damaged kerb and channel on Coburn Avenue. Close to corner. In front of storm water pit. As marked in the rain.
159251 | a_Outfall | 216014.0556 | OFT01 OFT01 - Open Outfall | Outfall | expose outfall on beach opp penny lane McCrae. On point nepean rd |  |  |  | COMPLETED | 2016-11-21 11:54 | Jane.Piotrowski | 2016-12-08 08:33 | 2016-11-07 11:54 | Alistair.White |  |  | 1 | LINM | 1 | 14D | PERMANENT | LS |  |  | 2016-12-12 08:34 | 2016-12-12 08:34 | 10 | NA | 2016-12-12 08:35 | 2016-11-07 11:57 | 216004.0556 | OFALL | LS | OF01 | expose outfall on beach opp penny lane McCrae. On point nepean rd
159176 | a_Outfall | 216489.0556 | OFT01 OFT01 - Open Outfall | Outfall | outfall on beach blocked opp Margaret ave McCrae. enter via car park on beach Point Nepean Rd |  |  |  | COMPLETED | 2016-12-22 11:43 | Excavator1 | 2016-12-19 08:06 | 2016-12-08 11:43 | Alistair.White |  |  | 5 | LINM | 1 | 14D | PERMANENT | LS |  |  | 2016-12-20 08:06 | 2016-12-20 08:06 | 15 | NA | 2016-12-20 08:07 | 2016-12-08 11:45 | 216480.0556 | OFALL | LS | OF01 | outfall on beach blocked opp Margaret ave McCrae. enter via car park on beach.
6320 | Network | 215275.0562 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie McCrae | Patrol Crew made boardwalk safe |  |  | COMPLETED | 2017-02-08 13:55 | Michelle.Twaites | 2017-01-09 13:55 | 2017-01-09 13:55 | Michelle.Twaites | 2017-02-08 13:55 |  | 1 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2017-01-10 13:57 | 2017-01-10 13:57 | 214631.0562 | BWALK | LS | BW02 | The Eyrie McCrae | Patrol Crew made boardwalk safe
6320 | Network | 215276.0562 | MST08 MST08 - Errect Signage | Make Safe | The Eyrie McCrae | 9/1 Patrol Crew erected a PWYS sign and will return for repairs (215275.0562) 10.1 |  |  | COMPLETED | 2017-01-10 14:44 | Michelle.Twaites | 2017-01-09 14:44 | 2017-01-09 14:44 | Michelle.Twaites | 2017-01-10 14:44 |  | 1 | ITEM | 1 | 1D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2017-01-10 14:49 | 2017-01-10 14:49 | 214632.0562 | MSAFE | LS | MS01 | The Eyrie McCrae | 9/1 Patrol Crew erected a PWYS sign and will return for repairs (215275.0562) 10.1
6320 | Network | 214506.0548 | BWT02 BWT02 - Replace Bolts or Nails | Board Walk, Jetty, LookOut, Stairs | The Eyrie, MCCRAE | Patrol Crew attended and screwed in loose back board at top of stairs |  |  | COMPLETED | 2017-02-09 08:00 | Jane.Piotrowski | 2017-01-10 08:00 | 2017-01-10 08:00 | Jane.Piotrowski | 2017-02-09 08:00 |  | 1 | ITEM | 1 | 30D | FIND_N_FIX | LS |  |  | 2017-01-11 08:02 |  | 1 | NA | 2017-01-11 08:02 | 2017-01-11 08:02 | 214441.0548 | BWALK | LS | BW01 | The Eyrie, MCCRAE | Patrol Crew attended and screwed in loose back board at top of stairs
6833 | Network | 214661.0557 | LDT02 LDT02 - Provisional Works | Lined Drain | 2 View Point Rd & Prospect Hill Rd McCrae | Upgrade the 225mm pipeline at intersection with a 300mm black max pipeline Raise road reserve along Prospect Hill Rd to protect property Build a levy bank at the back of the SEP in Prospect Hill Rd in front of the gates (levy will be high than gates preventing usage) Reconnect disused SEP in View Point Rd with flutes & create levy at rear to protect lower property | 2017-05-03 12:59 | Andrew.Taylor | COMPLETED | 2022-05-03 08:21 | Michelle.Twaites | 2017-05-30 09:16 | 2017-05-03 08:29 | Andrew.Taylor | 2022-05-03 12:59 |  | 36 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 2017-05-31 09:16 | 2017-05-31 09:16 | 36 | NA | 2017-05-31 09:17 | 2017-05-03 08:30 | 214650.0557 | LDRAIN | PW | LD04 | 2 View Point Rd & Prospect Hill Rd McCrae | Upgrade the 225mm pipeline at intersection with a 300mm black max pipeline Raise road reserve along Prospect Hill Rd to protect property Build a levy bank at the back of the SEP in Prospect Hill Rd in front of the gates (levy will be high than gates preventing usage) Reconnect disused SEP in View Point Rd with flutes & create levy at rear to protect lower property
6320 | Network | 217754.0554 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replaced damaged kerb and channel o/s # 1 The Eyrie corner Wonga Grove, McCrae. Damaged kerb and channel on the corner. Marked in the rain. |  | 2017-09-13 09:00 | Martin.Byrne | COMPLETED | 2027-08-11 13:40 | Mark.Coward | 2019-08-03 10:32 | 2017-08-11 13:42 | Gerard.Pillay | 2027-09-13 09:00 |  | 16 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 16 | NA | 2019-08-03 10:34 | 2017-08-11 13:43 | 217692.0554 | NKR | PM | KC02 | Replaced damaged kerb and channel o/s # 1 The Eyrie corner Wonga Grove, Maccrae. Damaged kerb and channel on the corner. Marked in the rain.
6320 | Network | 2354.0565 | RPT02 RPT02 - Repair Edge Break | A4.12 Edge Break Repair | cnr THE EYRIE & WONGA GV | Repair edge break & k&c while waiting for replacement. |  |  | COMPLETED | 2018-06-07 13:26 | Flocon1 | 2018-05-16 09:13 | 2018-02-07 13:26 | Mark.Coward |  |  | 1.5 | LINM | 1 | 120D | PERMANENT | LS |  |  | 2018-05-16 09:13 | 2018-05-16 09:13 | 1.5 | NA | 2018-05-16 09:14 | 2018-02-07 13:29 | 2365.0565 | SEB | LS | RP02 | cnr THE EYRIE & WONGA GV | Repair edge break & k&c while waiting for replacement.
6320 | Network | 218862.0553 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie McCrae | 16/3 Patrol Crew attended and replaced 5 tread boards. |  |  | COMPLETED | 2018-04-15 11:50 | Carly.McCrohan | 2018-03-16 11:51 | 2018-03-16 11:51 | Carly.McCrohan | 2018-04-15 11:50 |  | 1 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2018-03-20 11:52 | 2018-03-20 11:52 | 216534.0553 | BWALK | LS | BW02 | The Eyrie McCrae | 16/3 Patrol Crew attended and replaced 5 tread boards.
2077 | Network | 217602.0555 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie Stairs, MCCRAE | Response crew to replace tread as marked and have a look at missing bolts. |  |  | COMPLETED | 2018-04-26 15:02 | Patrol1 | 2018-04-04 09:55 | 2018-03-27 15:03 | Natalie.Renouf | 2018-04-26 15:03 |  | 1 | LINM | 1 | 30D | PERMANENT | LS |  |  | 2018-04-04 09:55 | 2018-04-04 09:55 | 1 | NA | 2018-04-04 09:56 | 2018-03-27 15:09 | 217433.0555 | BWALK | LS | BW02 | The Eyrie Stairs, MCCRAE | Response crew to replace tread as marked and have a look at missing bolts.
2077 | Network | 274.057 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | The Eyrie, MCCRAE | Patrol Crew replaced 1 x damaged treadboard on The Eyrie Steps as find & fix |  |  | COMPLETED | 2018-07-13 15:38 | Jane.Piotrowski | 2018-06-13 15:38 | 2018-06-13 15:40 | Jane.Piotrowski | 2018-07-13 15:40 |  | 2 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 2 | NA | 2018-06-13 15:41 | 2018-06-13 15:41 | 49.057 | BWALK | LS | BW02 | The Eyrie, MCCRAE | Patrol Crew replaced 1 x damaged treadboard on The Eyrie Steps as find & fix
6320 | Network | 1.4159 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | 15 The Eyrie, MCCRAE | Crew attended location and replaced step boards Merit 2027377 |  |  | COMPLETED | 2019-02-15 09:39 | Kylie.Crow1 | 2019-01-16 09:42 | 2019-01-16 09:42 | Kylie.Crow1 | 2019-02-15 09:39 |  | 4 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 4 | NA | 2019-01-17 09:43 | 2019-01-17 09:43 | 1.4159 | BWALK | LS | BW02 | 15 The Eyrie, MCCRAE | Crew attended location and replaced step boards Merit 2027377
6320 | Network | 220189.0553 | BWT03 BWT03 - Replace Timber | Board Walk, Jetty, LookOut, Stairs | 15 The Eyrie MCCRAE | RRT attended and fixed the step |  |  | COMPLETED | 2019-02-17 16:00 | Carly.McCrohan | 2019-01-18 16:01 | 2019-01-18 16:01 | Carly.McCrohan | 2019-02-17 16:00 |  | 1 | LINM | 1 | 30D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2019-01-21 16:03 | 2019-01-21 16:03 | 217046.0553 | BWALK | LS | BW02 | 15 The Eyrie MCCRAE | RRT attended and fixed the step
4301 | Network | 790.0574 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | Pothole repairs o/s 1 Prospect Hill Rd, cnr Coburn Ave McCrae. Marked. Damaged asphalt on Prospect Hill Rd | Please remove loose sections of damaged asphalt. Refer to pictures |  |  | COMPLETED | 2019-02-19 12:12 | David.Norton | 2019-02-06 15:43 | 2019-02-05 12:16 | Gerard.Pillay | 2019-02-19 12:16 |  | 2.42 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2019-02-06 15:43 | 2019-02-06 15:43 | 2.42 | NA | 2019-02-06 15:44 | 2019-02-05 12:17 | 774.0574 | PPR | LS | RP01 | Pothole repairs o/s 1 Prospect Hill Rd, cnr Coburn Ave McCrae. Marked. Damaged asphalt on Prospect Hill Rd | Please remove loose sections of damaged asphalt. Refer to pictures
6833 | Network | 791.0574 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace damaged k & c o/s 1 View Pt Rd McCrae.cnr Prospect Hill Rd, in View Pt side. Marked |  | 2019-02-15 13:33 | Chris.Godsil | AVAILABLE | 2019-04-06 12:28 |  |  | 2019-02-05 12:32 | Gerard.Pillay | 2029-02-15 13:33 |  | 6 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 6 | NA |  | 2019-02-05 12:33 | 775.0574 | NKR | LS | KC02 | Replace damaged k & c o/s 1 View Pt Rd McCrae.cnr Prospect Hill Rd, in View Pt side. Marked
4795 | Network | 214779.0545 | URT01 URT01 - Gravel Patch | Unsealed Road Pavement | At entrance to Margaret Street | Gravel patch holes at entrance Merit # 2045516 |  |  | COMPLETED | 2019-03-27 13:02 | Bobcat1 | 2019-02-28 13:03 | 2019-02-27 13:04 | Mark.Venturin | 2019-03-27 13:02 |  | 20 | SQM | 1 | 28D | PERMANENT | LS |  |  | 2019-02-28 13:03 | 2019-02-28 13:03 | 40 | NA | 2019-02-28 13:03 | 2019-02-27 13:07 | 214795.0545 | UPAVT | LS | UR05 | At entrance to Margaret Street | Gravel patch holes at entrance Merit # 2045516
1938 | Network | 214814.0545 | URT01 URT01 - Gravel Patch | Unsealed Road Pavement | Penny Lane (West) | Gravel Patch as required please include area around to the Left Merit # 2055329 |  |  | COMPLETED | 2019-04-24 14:18 | Bobcat1 | 2019-03-29 12:46 | 2019-03-27 14:24 | Mark.Venturin | 2019-04-24 14:18 |  | 200 | SQM | 1 | 28D | PERMANENT | LS |  |  | 2019-03-29 12:46 | 2019-03-29 12:46 | 200 | NA | 2019-03-29 12:47 | 2019-03-27 14:25 | 214828.0545 | UPAVT | LS | UR05 | Penny Lane (West) | Gravel Patch as required please include area around to the Left Merit # 2055329
4301 | Network | 133.4157 | PTT06 PTT06 - Reset Lid | A4.18 Pit / Drainage Structure Repair | 11 Prospect Hill Road, MCCRAE | RRT Sth attended location and reset pit lid back into place. Merit2070668 |  |  | COMPLETED | 2019-05-08 15:59 | Rachel.Larsen | 2019-05-08 12:01 | 2019-05-08 12:01 | Rachel.Larsen | 2019-05-22 12:01 |  | 1 | ITEM | 1 | 14D | FIND_N_FIX | LS |  |  |  |  | 1 | NA | 2019-05-09 12:02 | 2019-05-09 12:02 | 103.4157 | DPR | LS | PT04 | 11 Prospect Hill Road, MCCRAE | RRT Sth attended location and reset pit lid back into place. Merit2070668
222800 | a_FootpathLow | 220262.0552 | SRT06 SRT06 - Concrete Replacement | A4.22 Maintenance of Path | Replace 2 cracking concrete steps 20m from the top of The Eyrie Steps public walk-way . |  |  |  | AVAILABLE | 2019-06-28 13:05 |  |  | 2019-05-29 13:08 | Gerard.Pillay | 2029-05-29 13:08 |  | 1.5 | SQM |  | 10Y | PERMANENT | PM |  |  |  |  | 1.5 | NA |  | 2019-05-29 13:09 | 220266.0552 | RFK | LS | SR02 | Replace 2 cracking concrete steps 20m from the top of The Eyrie Steps public walk-way .
4795 | Network | 41.0591 | LDT02 LDT02 - Provisional Works | Lined Drain | 4 Margaret St McCrae | Repair to the 600mm pipeline & create bund wall to protect property |  |  | COMPLETED | 2024-06-06 07:32 | Andrew.Taylor | 2019-07-03 12:00 | 2019-07-03 07:33 | Andrew.Taylor | 2024-07-03 07:33 |  | 4.8 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 2019-06-16 12:00 | 2019-07-03 12:00 | 4.8 | NA | 2019-11-21 10:03 | 2019-11-21 07:35 | 42.0591 | LDRAIN | PW | LD04 | 4 Margaret St McCrae | Repair to the 600mm pipeline & create bund wall to protect property
8177 | Network | 1451.0593 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | 1 x shallow pothole o/s # 3 Penny lane . Marked in rain |  |  |  | COMPLETED | 2019-12-10 10:29 | Flocon1 | 2019-11-28 10:59 | 2019-11-26 10:31 | Glenn.Richardson2 | 2019-12-10 10:31 |  | 0.4 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2019-11-28 10:59 | 2019-11-28 10:59 | 0.4 | NA | 2019-11-28 10:59 | 2019-11-26 10:32 | 1447.0593 | PPR | LS | RP01 | 1 x shallow pothole o/s # 3 Penny lane . Marked in rain
8177 | Network | 1452.0593 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | 1 x shallow pothole o/s # 5a Penny lane . |  |  |  | COMPLETED | 2019-12-10 10:33 | Flocon1 | 2019-11-28 10:59 | 2019-11-26 10:34 | Glenn.Richardson2 | 2019-12-10 10:34 |  | 0.1 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2019-11-28 10:59 | 2019-11-28 10:59 | 0.1 | NA | 2019-11-28 10:59 | 2019-11-26 10:35 | 1448.0593 | PPR | LS | RP01 | 1 x shallow pothole o/s # 5a Penny lane .
8177 | Network | 1453.0593 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | 1 x pothole opp # 1 Penny Lane . |  |  |  | COMPLETED | 2019-12-10 10:37 | Flocon1 | 2019-11-28 10:55 | 2019-11-26 10:38 | Glenn.Richardson2 | 2019-12-10 10:38 |  | 0.3 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2019-11-28 10:55 | 2019-11-28 10:55 | 0.3 | NA | 2019-11-28 10:56 | 2019-11-26 10:38 | 1449.0593 | PPR | LS | RP01 | 1 x pothole opp # 1 Penny Lane .
5658 | Network | 901.057 | AHT04 AHT04 - Provide Assistance - Other | After Hours | Corner Charlesworth & Henry, MCCRAE | After Hours Callout ID: 22178521 GR attended, tree is too high. Phoned through to Parks Team |  |  | COMPLETED | 2019-12-30 02:55 | Jane.Piotrowski | 2019-12-29 10:56 | 2019-12-29 10:56 | Jane.Piotrowski | 2019-12-30 02:56 |  | 1.45 | HRS | 1 | 16H | FIND_N_FIX | LS |  |  |  |  | 1.45 | NA | 2019-12-30 10:57 | 2019-12-30 10:57 | 527.057 | AHOUR | LS | AH02 | Corner Charlesworth & Henry, MCCRAE | After Hours Callout ID: 22178521 GR attended, tree is too high. Phoned through to Parks Team
6320 | Network | 243.0591 | BWT09 BWT09 - Provisional Works | Board Walk, Jetty, LookOut, Stairs | The Eyrie McCrae - Stairs | Remove the rotted and failing timber edge strips to the concrete steps & replace with new timbers |  |  | COMPLETED | 2025-01-27 09:08 | Andrew.Taylor | 2020-03-03 12:00 | 2020-01-27 09:10 | Andrew.Taylor | 2025-01-27 09:10 |  | 8 | ITEM | 1 | 5Y | PERMANENT | PW |  |  | 2020-01-30 12:00 | 2020-03-03 12:00 | 8 | NA | 2020-03-31 09:42 | 2020-03-31 09:11 | 246.0591 | BWALK | PW | BW05 | The Eyrie McCrae - Stairs | Remove the rotted and failing timber edge strips to the concrete steps & replace with new timbers
6320 | Network | 2034.0593 | KCT05 KCT05 - Concrete Replacement | A4.23 Kerb & Channel Repairs | Replace 2m f damaged kerb & channel on cnr of Wonga gv & The Eyrie . |  |  |  | AVAILABLE | 2020-04-20 09:28 |  |  | 2020-02-20 09:30 | Glenn.Richardson2 | 2030-02-20 09:30 |  | 2 | LINM | 1 | 10Y | PERMANENT | PM |  |  |  |  | 2 | NA |  | 2020-02-20 09:30 | 2029.0593 | NKR | LS | KC02 | Replace 2m f damaged kerb & channel on cnr of Wonga gv & The Eyrie .
4301 | Network | 2035.0593 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | 1 x pothole , beside kerb , o/s # 14 Prospect Hill rd . |  |  |  | COMPLETED | 2020-03-05 09:34 | Flocon1 | 2020-03-04 13:54 | 2020-02-20 09:35 | Glenn.Richardson2 | 2020-03-05 09:35 |  | 0.8 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2020-03-04 13:54 | 2020-03-04 13:54 | 0.8 | NA | 2020-03-04 13:55 | 2020-02-20 09:36 | 2030.0593 | PPR | LS | RP01 | 1 x pothole , beside kerb , o/s # 14 Prospect Hill rd .
1938 | Network | 215310.0545 | URT01 URT01 - Gravel Patch | Unsealed Road Pavement | Penny Lane, West | M# 2203318 Gravel patch potholes as needed - allow little topper load of rock |  |  | COMPLETED | 2020-06-30 09:47 | Bobcat1 | 2020-06-10 08:40 | 2020-06-02 09:49 | Mark.Venturin | 2020-06-30 09:47 |  | 80 | SQM | 1 | 28D | PERMANENT | LS |  |  | 2020-06-10 07:30 | 2020-06-10 08:40 | 80 | NA | 2020-06-10 08:41 | 2020-06-02 09:51 | 215334.0545 | UPAVT | LS | UR05 | Penny Lane, West | M# 2203318 Gravel patch potholes as needed - allow little topper load of rock
1938 | Network | 478.0571 | RPT01 RPT01 - Repair Pothole | A4.7 Pothole Repair | car park opp Penny lane Mccrae | car park opp Penny Lane ,drive in to car park the first parking spot on your right 1mt x2.5 were edge has broken away ,merit 2278556 |  |  | COMPLETED | 2021-01-20 14:13 | Flocon1 | 2021-01-15 09:08 | 2021-01-06 14:16 | Neil.Robertson | 2021-01-20 14:13 |  | 4 | SQM | 1 | 14D | PERMANENT | LS |  |  | 2021-01-15 09:08 | 2021-01-15 09:08 | 4 | NA | 2021-01-15 09:08 | 2021-01-06 14:18 | 484.0571 | PPR | LS | RP01 | car park opp Penny lane Mccrae | car park opp Penny Lane ,drive in to car park the first parking spot on your right 1mt x2.5 were edge has broken away ,merit 2278556
159176 | a_Outfall | 113.0594 |  | DOD - Clear Open Drains | Outfall opposite Margaret Ave | M#2311033 Clear outfall buried by reclaimed sand |  |  | COMPLETED | 2021-03-25 14:16 | .SUB CONTRACTOR | 2021-03-24 15:56 | 2021-03-24 14:17 | Kim.Whiting | 2021-03-25 14:17 |  | 10 | LINM | 1 | 1WD | PERMANENT | LUMP_SUM |  |  | 2021-03-24 15:56 | 2021-03-24 15:56 | 10 | NA | 2021-03-18 17:47 | 2021-03-24 14:21 | 113.0594 | 2007 | LUMP_SUM | DOD01 | Outfall opposite Margaret Ave
4301 | Network | 643.0571 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | Prospect Hill Rd, Mccrae | Repair pothole O/S #1 merit #2317841 |  |  | COMPLETED | 2021-04-28 14:21 | Flocon1 | 2021-04-19 14:00 | 2021-04-14 14:23 | Neil.Robertson | 2021-04-28 14:21 |  | 1 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2021-04-19 14:00 | 2021-04-19 14:00 | 1 | NA | 2021-04-19 14:00 | 2021-04-14 14:24 | 651.0571 | 2010 | LUMP_SUM | PPR01 | Prospect Hill Rd, Mccrae | Repair pothole O/S #1 merit #2317841
8177 | Network | 6103.0593 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | o/s # 5a Penny Lane . | 1 x pothole . |  |  | COMPLETED | 2021-06-07 14:01 | Flocon1 | 2021-06-03 08:58 | 2021-05-24 14:02 | Glenn.Richardson2 | 2021-06-07 14:02 |  | 0.2 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2021-06-03 08:58 | 2021-06-03 08:58 | 0.2 | NA | 2021-06-03 08:58 | 2021-05-24 14:03 | 6099.0593 | 2010 | LUMP_SUM | PPR01 | o/s # 5a Penny Lane . | 1 x pothole .
1938 | Network | 6750.0593 | PGU01 PGU01 - Gravel Patch | PGU - Grading Unsealed roads | On Penny Lane west 20m in from Pt Nepean Rd | Bobcat gravel patching required to fill potholes . 3 or 4 buckets required . |  |  | COMPLETED | 2021-09-13 09:18 | Bobcat1 | 2021-08-20 10:23 | 2021-08-16 09:25 | Glenn.Richardson2 | 2021-09-13 09:25 |  | 50 | LINM | 1 | 28D | PERMANENT | LUMP_SUM |  |  | 2021-08-20 10:23 | 2021-08-20 10:53 | 50 | NA | 2021-08-20 10:53 | 2021-08-16 09:25 | 6745.0593 | 2022 | LUMP_SUM | PGU01 | On Penny Lane west 20m in from Pt Nepean Rd | Bobcat gravel patching required to fill potholes . 3 or 4 buckets required .
170536 | a_Stairs | 422.0613 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | 22 The Eyrie McCrae | Replace 2x Timbers. Marked. Merit #2428553 & #2430785 |  |  | COMPLETED | 2022-04-06 13:54 | .CREW MAINTENANCE | 2022-04-06 07:29 | 2022-03-07 13:55 | Neil.Robertson | 2022-04-06 13:55 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-04-06 07:29 | 2022-04-06 07:29 | 1 | NA | 2022-04-06 07:30 | 2022-03-07 13:56 | 425.0613 | 2021 | LUMP_SUM | RFK01 | 22 The Eyrie McCrae | Replace 2x Timbers. Marked. Merit #2428553
170536 | a_Stairs | 255.0609 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | The Eyrie Stairs McCrae | RRT replaced 1 x tread |  |  | COMPLETED | 2022-07-15 16:40 | .CREW MAINTENANCE | 2022-07-01 16:43 | 2022-07-01 16:41 | Michelle.Twaites | 2022-07-31 16:41 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-07-01 16:42 | 2022-07-01 16:43 | 1 | NA | 2022-07-04 16:43 | 2022-07-04 16:42 | 253.0609 | 2021 | LUMP_SUM | RFK01 | The Eyrie Stairs McCrae | RRT replaced 1 x tread
1938 | Network | 222668.0552 | PGU01 PGU01 - Gravel Patch | PGU - Grading Unsealed roads | Penny Lane West McCrae | Add rock to laneway when dryer. Large potholing occurring. M2464359 |  |  | COMPLETED | 2022-08-05 12:17 | Bobcat1 | 2022-08-08 09:07 | 2022-07-08 12:17 | Courtney.Verhagen | 2022-08-05 12:17 |  | 100 | LINM | 1 | 28D | PERMANENT | LUMP_SUM |  |  | 2022-08-08 08:43 | 2022-08-08 09:07 | 100 | NA | 2022-08-08 09:07 | 2022-07-08 12:18 | 222655.0552 | 2022 | LUMP_SUM | PGU01 | Penny Lane West McCrae | Add rock to laneway when dryer. Large potholing occurring. M2464359
6320 | Network | 1820.0569 | MEC01 MEC01 - Make Safe | MEC - Call Out Service | 17 The Eyrie, Mccrae | Sink hole in driveway made safe with stake and parawebbing by Rapid South. M#2485946. |  |  | COMPLETED | 2022-09-20 11:11 | .CREW MAINTENANCE | 2022-09-14 10:09 | 2022-09-14 10:09 | Kylie.Crow1 | 2022-09-20 11:11 |  | 1 | HRS | 1 | 1H | FIND_N_FIX | LUMP_SUM |  |  | 2022-09-14 10:06 | 2022-09-14 10:09 | 1 | NA | 2022-09-20 10:11 | 2022-09-20 10:11 | 1757.0569 | 2001 | LUMP_SUM | MEC01
6518 | a_Pipe | 948.0591 | DLD03 DLDT03 - Repair Lined Drain | DLD - Minor Repair Lined Drains | 17 The Eyrie McCrae | Investigated sink hole in driveway & found pipe displacement. Repaired & reinstated all areas effected (ID: 2485946) |  |  | COMPLETED | 2022-11-02 07:25 | Andrew.Taylor | 2022-10-12 07:31 | 2022-10-03 07:27 | Andrew.Taylor | 2022-11-02 07:27 |  | 2.4 | LINM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2022-10-11 07:30 | 2022-10-12 07:31 | 2.4 | NA | 2022-10-12 07:31 | 2022-10-12 07:30 | 933.0591 | 2006 | LUMP_SUM | DLD01 | 17 The Eyrie McCrae | Investigated sink hole in driveway & found pipe displacement. Repaired & reinstated all areas effected (ID: 2485946)
1938 | Network | 60.4148 | PGU01 PGU01 - Gravel Patch | PGU - Grading Unsealed roads | Penny lane West, mccrae | S/s to add rock and repair pot holes |  |  | COMPLETED | 2022-11-22 08:09 | Bobcat1 | 2022-11-30 11:43 | 2022-10-25 08:10 | G_MPSC_ShoulderGrading | 2022-11-22 08:10 |  | 40 | LINM | 1 | 28D | PERMANENT | LUMP_SUM |  |  | 2022-11-30 10:36 | 2022-11-30 11:43 | 40 | NA | 2022-11-30 11:43 | 2022-10-25 08:10 | 20.4148 | 2022 | LUMP_SUM | PGU01 | Penny lane West, mccrae | S/s to add rock and repair pot holes
1938 | Network | 1954.0569 | MEC01 MEC01 - Make Safe | MEC - Call Out Service | Penny Lane McCrae | M#2505684 Call out id 31685288 A/hrs attended location and SES and Shire were already onsite, nfa req |  |  | COMPLETED | 2022-11-15 17:28 | Kylie.Crow1 | 2022-11-21 16:30 | 2022-11-15 16:29 | Kylie.Crow1 | 2022-11-15 17:29 |  | 1 | HRS | 1 | 1H | PERMANENT | LUMP_SUM |  |  | 2022-11-21 16:29 | 2022-11-21 16:30 | 1 | NA | 2022-11-21 16:30 | 2022-11-21 16:30 | 1891.0569 | 2001 | LUMP_SUM | MEC01 | Penny Lane McCrae | M#2505684 Call out id 31685288 A/hrs attended location and SES and Shire were already onsite, nfa req
4301 | Network | 970.0613 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | prospect hill McCrae | please repair broken asphalt in front of #1 /merit 2514786 |  |  | COMPLETED | 2022-12-30 10:55 | Flocon1 | 2023-01-03 11:58 | 2022-12-16 10:58 | Neil.Robertson | 2022-12-30 10:55 |  | 2 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-01-03 11:48 | 2023-01-03 11:58 | 2 | NA | 2023-01-03 11:58 | 2022-12-16 10:59 | 994.0613 | 2010 | LUMP_SUM | PPR01 | prospect hill McCrae | please repair broken asphalt in front of #1 /merit 2514786
4301 | Network | 305.4179 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | 1 Prospect Hill Road McCrae | CLEAN 1x previous pothole repair and re do. M2514786 |  |  | COMPLETED | 2023-02-07 13:56 | Flocon1 | 2023-02-03 10:40 | 2023-01-24 13:58 | Courtney.Verhagen | 2023-02-07 13:58 |  | 0.1 | SQM | 1 | 14D | PERMANENT | LUMP_SUM |  |  | 2023-02-03 10:20 | 2023-02-03 10:40 | 0.1 | NA | 2023-02-03 10:41 | 2023-01-24 13:59 | 308.4179 | 2010 | LUMP_SUM | PPR01 | 1 Prospect Hill Road McCrae | CLEAN 1x previous pothole repair and re do. M2514786
1938 | Network | 199.4178 | PGU01 PGU01 - Gravel Patch | PGU - Grading Unsealed roads | Penny Lane West | Merit /: 2571866 . Please cut , add rock and gravel to repair low points in the lane |  |  | COMPLETED | 2023-07-21 12:04 | Bobcat1 | 2023-07-15 08:29 | 2023-06-23 12:07 | G_MPSC_Spraying | 2023-07-21 12:07 |  |  | LINM | 1 | 28D | PERMANENT | LUMP_SUM |  |  | 2023-07-15 07:00 | 2023-07-15 08:29 | 80 | NA | 2023-07-15 08:30 | 2023-06-23 12:07 | 197.4178 | 2022 | LUMP_SUM | PGU01 | Penny Lane West | Merit /: 2571866 . Please cut , add rock and gravel to repair low points in the lane
63930 | a_Pit | 1519.4201 | DPR10 DPR10 - Make Safe | DPR - Pit/Drainage Structure Repair | 17 The Eyrie MCCRAE | Rapid SOuth attended and advised made safe with stake and tape. 005505 |  |  | COMPLETED | 2023-10-26 19:30 | G_MPSC_RapidSouth1 | 2023-10-26 15:00 | 2023-10-26 14:40 | Lalah.Farhang | 2023-10-26 18:40 |  | 1 | ITEM | 1 | 4H | PERMANENT | LUMP_SUM |  |  | 2023-10-26 14:40 | 2023-10-26 15:00 | 1 | NA | 2023-10-26 15:32 | 2023-10-26 15:34 | 1057.4201 | 2008 | LUMP_SUM | DPR01 | 17 The Eyrie MCCRAE | new lid required. 005505
63930 | a_Pit | 1518.4201 | DPR01 DPR01 - Replace Lid | DPR - Pit/Drainage Structure Repair | 17 The Eyrie MCCRAE | new lid required. 005505 |  |  | AVAILABLE | 2023-10-26 19:30 |  |  | 2023-10-26 15:31 | Lalah.Farhang | 2033-10-26 15:31 |  | 1 | ITEM |  | 10Y | PERMANENT | SOR | [5 empty] | NA |  | 2023-10-26 15:32 | 1057.4201 | 2008 | LUMP_SUM | DPR01 | 17 The Eyrie MCCRAE | new lid required. 005505
159897 | a_Carpark | 181.0632 | PPR01 PPR01 - Repair Pothole | PPR - Pothole Repair | Located at McCrae Foreshore Carpark Opposite Penny Lane, McCrae | 7 x approx p/h repairs, not marked due to rain. |  |  | COMPLETED | 2023-12-18 11:50 | Flocon1 | 2023-12-15 12:05 | 2023-12-11 11:52 | Piper-Lily.Egan | 2023-12-18 11:52 |  | 0.7 | SQM | 1 | 7D | PERMANENT | LUMP_SUM |  |  | 2023-12-15 10:55 | 2023-12-15 12:05 | 0.7 | NA | 2023-12-15 14:57 | 2023-12-11 11:52 | 182.0632 | 2010 | LUMP_SUM | PPR01 | Located at McCrae Foreshore Carpark Opposite Penny Lane, McCrae | 7 x approx p/h repairs, not marked due to rain.
170536 | a_Stairs | 1114.4179 | RFK11 RFK11 - Replace Timbers | RFK - Maintenance of Paths | 20-22 The Eyrie Stairs McCrae | Replace 3x timbers along front of concrete stairs. . approx 1350x75x200. 010546 |  |  | COMPLETED | 2024-03-17 14:41 | Patrol1 | 2024-03-14 10:31 | 2024-02-16 14:42 | Courtney.Verhagen | 2024-03-17 14:42 |  | 1 | ITEM | 1 | 30D | PERMANENT | LUMP_SUM |  |  | 2024-03-14 08:45 | 2024-03-14 10:31 | 1 | NA | 2024-03-14 10:31 | 2024-02-16 14:44 | 1119.4179 | 2021 | LUMP_SUM | RFK01 | 20-22 The Eyrie Stairs McCrae | Replace 3x timbers along front of concrete stairs. . approx 1350x75x200. 010546