## Charlesworth
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: Charlesworth Street
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M095581 | REQ: 123526 Road Maintenance | 2024-12-12 11:00 | All | Complete | 2024-11-28 | REQ: 123526 Reference: 2024-099104 Address: 3 Charlesworth Street MCCRAE VICTORIA 3938 GIS image attached Customer reporting a sinkhole has appeared on the road in front of her house approx a dinner plate in diameter, reports it is leaking with water, please attend ASAP. Thanks | erected traffic hazard signs and cone in road as we waited for south east water to arrive
M103841 | REQ: 131164 Stormwater Drainage Concern | 2025-01-10 11:00 | All | Complete | 2024-12-20 | REQ: 131164 Reference: 2024-106738 Address: 1 Charlesworth Street MCCRAE VICTORIA 3938 Caller Reporting A Large Amount Of Groundwater Streaming Out Of The Road At This Location. Caller Reports South East Water Have Attended And Confirmed It Isn't A Burst Main. Caller Advises It Is A Danger To Residents And Public, As This May Be Unstable Ground, And This Is The Only Passage Out For Some Residents. | Put bollards and tape around affected area

## Prospect Hill
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: Prospect Hill Road
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M127035 | REQ: 142472 Road Maintenance | 2025-02-05 11:00 | All | Complete | 2025-01-22 | REQ: 142472 Reference: 2025-008559 Address: 5 Prospect Hill Road MCCRAE VICTORIA 3938 Customer reports holes in the road on Coburn Avenue, customer states that due to the high volume of traffic the road is breaking up and too many people using his road Prospect Hill Road due to the detour and are driving too fast. Customer reports traffic management is required. Thanks | FH and MPSC met with this customer on site 21/01/2025. Quote supplied to MPSC to do temp repair on Coburn Rd on 21/01/2025 under ordered works
M039247 | REQ: 81623 9 Prospect Hill Rd McCrae | 2024-08-06 10:00 | All | Complete | 2024-09-26 | REQ: 81623 Reference: 2024-057225 Address: 9 Prospect Hill Rd, McCrae VIC 3938, Australia | Attended prospect Hill Road finding branch in photo provided within CRM has already been removed from this location. Please SMS customer advising branch already removed as requested in CRM .

## View Point
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: View Point Road
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M041866 | REQ: 84206 1 Coburn Avenue MCCRAE | 2024-08-14 10:00 | All | Complete | 2024-11-26 | REQ: 84206 Reference: 2024-059804 Address: 1 Coburn Avenue MCCRAE VICTORIA 3938 **Snap, send & solve** Customer reporting trees and shrubs located at the intersection of Coburn Avenue & Point Nepean Road MCCRAE - 'Blocked view of oncoming traffic - This applies to many of the exits from the foreshore. You have to be out very close to passing traffic before you can see what's coming' Please investigate and make safe asap - thanks. | Attended intersection of Coburn Avenue and point Nepean Road finding area shown in photos provided by customer has just been recently cut back with all other exits from the bushland area in the process of being cut back or have been cut back. No contact requested in CRM no further action required. R.R
M128638 | REQ: 141901 Stormwater Drainage Concern | 2025-02-04 11:00 | Steven Fero | Not Started |  | REQ: 141901 Reference: 2025-007988 Address: 15 Coburn Avenue MCCRAE VICTORIA 3938 I have a house at 15 Coburn av. I have done extensive work to capture road water run off from View Point road. However street runoff comes down a cascade over a totally blocked grate it them runs down the hill to my property. The stairs going up the Margaret lane track are in very bad repair. This whole area needs a total rework. Could this be included in the work you are now doing in this area.
M092628 | REQ: 118124 Stormwater Drainage Concern | 2024-11-27 11:00 | All | Complete | 2024-11-22 | FH invest’n 22/11 ongoing **FH CUSTOMER CONTACT REQUIRED**REQ: 118124 Reference: 2024-093705 Address: 18-20 View Point Road MCCRAE VICTORIA 3938 Currently we have a case number 2024-081662 which was first reported on 09/10/24. I spoke to a council representative again today and urged her to follow up as no action has been taken yet. We were assured originally that action would be taken within 14 working days? We are still seeing an increase in surface water on our block which may is having a negative impact on our retaining wall. We fear given the historic land slip at 10-12 View Point Road that the remedial works undertaken in View Point Road above combined with 2 blocked drains are responsible for this water ingress. Please see attached images. We fear that if this issue is not attended to that this water ingress further degrade our retaining wall which is located within 3 metres of our house. Structural failure of this wall could result in significant damage t n | The blocked pits in question on View Point Road have already been entered on a previous work order as a defect 2024-081662 and are awaiting on approval and programming . Still to be completed. When these are clear it may solve some of the water ingress onto the property in question. The retaining wall in question will need an engineers report on its structural stability. Who has to organise and supply that as it’s not a MPS asset? The remedial works of the new kerb and channel and drainage scheme on View Point Road installed by MPS and its impact on land owners would all have been worked out in the planning process. Any information on this matter will have to be answered by the shire engineer who planned the works and they need to relay that information back to the resident on the capacity, flow and retention of water from the surrounding areas catchment and potential impact on residents.
M082454 | REQ: 106072 Stormwater Drainage Concern | 2024-10-23 11:00 | All | Complete | 2024-11-26 | Personal Information | vacuumed x2 pits and jetted 2 lines, all water flowing nicely
M073370 | REQ: 101348 Road Maintenance | 2024-10-08 10:00 | All | Complete | 2024-10-10 | TM - Lane inspected and forms part of the bobcat grading schedule - Waiting to be scheduled with traffic. Works to be completed by 31/10/2024 REQ: 101348 Reference: 2024-076943 Address: 1 Sumner Lane MORNINGTON VICTORIA 3931 In the lane there is a significant drop where bitumen meets gravel and an area of pooling water at this point which is very green with algae : a pedestrian has tripped today : please inspect with a view to filling the gap between the two surfaces and eliminating the tripping hazard | TM - Lane inspected and forms part of the bobcat grading schedule - Waiting to be scheduled with traffic. Works to be completed by 31/10/2024
M128039 | Lined Drain Repair |  | All | Complete | 2025-02-05 | PIPE REPAIR / EXTENSION REQUESTED URGENTLY- 300MM UP TO 3LM & CLEAR VEGETATION DOWN OUTLET STEPS CREATING A 1M CLEARANCE. Please provide option to patch concrete. REQ 025-009185 = the expulsion pipe at the end of the View Point Road McCrae drainage network is not diverting water into the open drain as intended. A repair or extension to the pipe and cleanup of the area to ensure it is working during low flows of storm water is required as a priority. | Completed by Bittern Earth Moving
M135908 | 12/02 - NDD - Non Destructive Digging |  | All | Complete | 2025-02-12 | NDD- (LAND SLIP) - 6 VIEW POINT RD, McCRAE - Defect Clear Culverts, Pipes and Pits .. Will need Impact Driver & 16" socket required to loosen the bolts to move the TEMP FENCING panels. Park slightly forward so as not to park directly under the overhead power line. .. vacuum excavation truck services (NDD) to be undertaken at 6 View Point Road .. • Depth – up to 3.2m below ground level to the invert of a sewer trench • Size – nom. 300mm diameter NDD hole • The services in the work area have been cleared by a service locator • The engineering firm will backfill the hole with sand and place a tarp on top of the hole for monitoring access later. • Note that at this stage there is no water or power available on site. I am working to gain access through the electric gates. • The vacuum truck can be set up in the driveway of 6 View Point Road. ... Waste to be assumed as contaminated... dispose of directly to waste disposal yard (NOT FH Depot) or on site if 1000 litre tubs are | Non-destructive digging into the ground 4 m deep the hole was also made safe with steak and tape and a board put over it for later to come back to Gma sucked everything out and also disposing of the waste at the Dandenong plant. See attached photos.
M092696 | 02/12- Clear Culverts, Pipes and Pits | 2024-12-15 11:26 | All | Complete | 2024-12-02 | VIEW POINT ROAD, MCRAE - Blocked pit Opposite No 10 and blocked pit throat at end of cul-de-sac. | vacuumed x2 pits at this location also jetted 2 lines, water flowing freely.

## Margaret
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: Margaret Street
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M128638 | REQ: 141901 Stormwater Drainage Concern | 2025-02-04 11:00 | Steven Fero | Not Started |  | REQ: 141901 Reference: 2025-007988 Address: 15 Coburn Avenue MCCRAE VICTORIA 3938 I have a house at 15 Coburn av. I have done extensive work to capture road water run off from View Point road. However street runoff comes down a cascade over a totally blocked grate it them runs down the hill to my property. The stairs going up the Margaret lane track are in very bad repair. This whole area needs a total rework. Could this be included in the work you are now doing in this area.

## The Eyrie
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: The Eyrie
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M044149 | REQ: 85412 Stormwater Drainage Concern | 2024-08-19 10:00 | All | Complete | 2024-08-06 | REQ: 85412 Reference: 2024-061010 Address: 17 The Eyrie MCCRAE VICTORIA 3938 old request 2023-005505 still has not been done drain cover surround to be replaced, make safe structure has collapsed please fix asap | Pit lid insert replaced at this location. pit surround was okay no damage

## Penny
My Work Order Listing
Parameters: Work System = CZZOPWORKS , Mode = WOL , External use = False , Restrict to current user = False , Work Execution = False
Criteria: Penny Lane
woWorkOrderNumber | woDescription | RequiredByDateTime | AssigneeDescription | SC_woWorkCompletionStatus | woActualFinishDate | woDetails | woComment | __md5Row
Work Order | Description | Required By | Assignee | Work Completion Status | Actual Finish Date | Details | Completion Comment
M128028 | 30/01-TM - Clear Culverts, Pipes & Pits | 2025-02-27 10:25 | All | Complete | 2025-01-30 | PIT CLEARING & JETTING - 613 PT NEPEAN RD, MCCRAE - Defect Clear Culverts, Pipes and Pits - 1/613 Point Nepean Road MCCRAE VICTORIA 3938 .. 28/01 - Site is already set to 40km/hr due to land slip. VicRoads blanket MOA to be used. Works are emergency works directed by Council relating to the Land Slip. REQ 025-009984 = The council drainage pit at Penny Lane access road is clogged and urgently requires cleaning and jetting of the discharge pipe to the Nepean highway | Sent to job at above adress where landslide has occurred Jetted line several times to clean line at councils request. Found that roots were obstructing line. Tried root cutting. Got 5 metres in line and found cutter not going any further. Pole camera used and found that line has collapsed in several places Time includes tooobox, travel, lunch and fill up of water tank. Traffic present to.
M073433 | Pothole Repair | 2024-10-10 10:59 | All | Complete | 2024-10-03 | Defect Pothole Repair - 4 x potholes o/s # 5a Penny Lane . | works completed 4 potholes filled
M102981 | REQ: 129836 Stormwater Drainage Concern | 2025-01-07 11:00 | Steven Fero | Not Started |  | FH 28/1 Still ongoing due to landslip, requires FH engineer on site with inspector. Being organised TT. was instructed to reassign to SF. REQ: 129836 Reference: 2024-105410 Address: 2 Penny Lane MCCRAE VICTORIA 3938 Refer Macrae Nov 2022 land slip Penny lane Macrae Spoon drains at the end of Penny lane once again full of water :,we have had little rain
M127738 | REQ: 143897 Stormwater Drainage Concern | 2025-02-10 11:00 | All | Complete | 2025-01-28 | REQ: 143897 Reference: 2025-009984 Address: 1/613 Point Nepean Road MCCRAE VICTORIA 3938 The council drainage pit at Penny Lane access road is clogged and urgently requires cleaning and jetting of the discharge pipe to the Nepean highway | 28/01 - Defect created for pit cleaning. refer to Defect 156601 / WO M128028

## Coburn
No relevant information located